## Sheet1
Bug ID | Bug Description | Steps | Expected Result | Actual Result | Severity (minor-major-critical) | Priority (high-medium-low) | Attachment | assign to | Status
1 | the password field not displayed when Manager open the URL (requirements issue) | 1-open URL ((https://demo.guru99.com/V4/ manager/addcustomerpage.php)) | all expected fields should be displayed | password filed also is display | minor | medium |  | Mostafa | new
2 | There is a default data for E-mail&password for the first loading | 1-open URL ((https://demo.guru99.com/V4/ manager/addcustomerpage.php)) | the fields haven't any data | E-mail and Password fields are have default data | minor | low |  | Mostafa | new
3 | Date of Birth accept wrong format | 1-open URL (https://demo.guru99.com/V4/ manager/addcustomerpage.php) 2- insert Date Of Birth -Date Of Birth:25/5/199999 | An error msg should be raised | the filed isn't accept data but return wrong error message ( Date Field must not be blank) | minor | low | Bugs\3.JPG | Alaa | new
4 | pin filed is treatment with space in the middle of it as character | 1-open URL (https://demo.guru99.com/V4/ manager/addcustomerpage.php) 2- insert pin -bin:6542 111 | the filed won't accept data and will return error message | the filed isn't accept data but return wrong error message (Characters are not allowed) | major | medium |  | Sayed | new
5 | when I add space in the middle of the mobile number filed I found filed see space in the middle as character | 1-open URL (https://demo.guru99.com/V4/ manager/addcustomerpage.php) 2- insert pin -mobile number:01142 676333 | the filed won't accept data and will return error message | the filed isn't accept data but return wrong error message ( Characters are not allowed) | major | medium |  | Sayed | new
6 | when I add wrong format for email id I found it accept wrong format | 1-open URL (https://demo.guru99.com/V4/ manager/addcustomerpage.php) 2- insert e-mail -E-mail: ahmed123@@gmail.com | the filed won't accept data and will return error message | the filed accept data | critical | high |  | Sayed | new
7 | when I add space for email address I found filed accept data | 1-open URL (https://demo.guru99.com/V4/ manager/addcustomerpage.php) 2- insert e-mail -E-mail:ahmed123@ gmail.com | the filed won't accept data and will return error message | the filed accept data | critical | high |  | Alaa | new
8 | when add space in the middle of customer id for edit customer I found filed treat with space as character | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :273 66 | the filed won't accept data and will return error message | the filed isn't accept data but return wrong error message (Characters are not allowed) | minor | low |  | Sayed | new
9 | when edit customer data I found wrong error message but data is changed successfully | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-edit address -address:24 qwity building 5-check customer again | (https://demo.guru99.com/V4/ manager/EditCustomer.php) -customer id :27366 -address:24 qwity building | the edit customer feature will change data and return confirmation message | major | medium |  | Sayed | new
10 | when edit customer for address I found error message and click submit data will delete | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove address filed 5-click submit 6- open same URL 7-insert customer id 8-click submit | the filed is mandatory and will return error message if left blank | the filed return error message (No Changes made to Customer records) but the data is deleted further filed is return error message (Address Field must not be blank) | critical | medium |  | Alaa | new
11 | when edit customer for city I found error message and click submit data will delete | 1-open URL https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove state filed 5-click submit 6- open same URL 7-insert customer id 8-click submit | the filed is mandatory and will return error message if left blank and not submit edit customer without it | the filed return error message (No Changes made to Customer records) but the data is removed further filed is return error message (city Field must not be blank) | critical | medium |  | Alaa | new
12 | when edit customer for state I found error message and click submit data will delete | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove state filed 5-click submit 6- open same URL 7-insert state 8-click submit | the filed is mandatory and will return error message if left blank and not submit edit customer without it | the filed return error message (No Changes made to Customer records) but the data is removed and edited further filed is return error message (state Field must not be blank) | critical | medium |  | Alaa | new
13 | when edit customer for pin I found error message and click submit data will delete | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove pin filed 5-click submit 6- open same URL 7-insert state 8-click submit | the filed is mandatory and will return error message if left blank and not submit edit customer without it | the filed return error message (No Changes made to Customer records) but the data is removed and edited further filed is return error message (PIN Code must not be blank) | critical | medium |  | Alaa | new
14 | when add space in the middle of customer id for edit customer I found filed treat with space as character | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-insert pin -pin:654 32 | the filed won't accept data and will return error message | the filed isn't accept data but return wrong error message (Characters are not allowed) | major | medium |  | Sayed | new
15 | when edit customer for mobile number I found error message and click submit data will delete | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove pin filed 5-click submit 6- open same URL 7-insert state 8-click submit | the filed is mandatory and will return error message if left blank and not submit edit customer without it | the filed return error message (No Changes made to Customer records) but the data is removed and edited further filed is return error message (PIN Code must not be blank) | critical | medium |  | Alaa | new
16 | when edit customer for email I found error message and click submit data will delete | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-remove email filed 5-click submit 6- open same URL 7-insert state 8-click submit | the filed is mandatory and will return error message if left blank and not submit edit customer without it | the filed return error message (No Changes made to Customer records) but the data is removed and edited further filed is return error message (Email-ID must not be blank) | critical | medium |  | Alaa | new
17 | when I add invalid email for edit customer filed accept data | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-insert email email:ahmed2@@.cada | the filed won't accept data and will return error message | the filed accept data | major | medium |  | Sayed | new
18 | when add email is already exist in the database and try to edit another customer then add existed email id to this new customer the mail will changed successfully | 1-open URL (https://demo.guru99.com/V4/ manager/EditCustomer.php) 2-insert customer id -customer id :27366 3-click submit 4-insert email email: alaa123@gmail.com | the filed won't accept data and will return error message | email accept to change with exist another email id | critical | high |  | Sayed | new
19 | when add space in the middle of customer id for delete customer I found filed treat with space as character | 1-open URL (https://demo.guru99.com/V4/manager/DeleteCustomerInput.php) 2-insert customer id -customer id : 36 90 3-click submit | the filed won't accept data and will return error message | the filed isn't accept data but return wrong error message (characters are not allowed) | major | medium |  | Mostafa | new
20 | when I delete invalid customer I found it return same message when I delete valid message | 1-open URL (https://demo.guru99.com/V4/manager/DeleteCustomerInput.php) 2-insert customer id -customer id : 3651390 3-click submit | the filed will return error message | the filed return same message when it delete successfully (Customer does not exist!!) | major | medium |  | Mostafa | new
21 | when I add space in the middle of customer id to create account num it treat with space as character | 1-open URL (https://demo.guru99.com/V4/ manager/addAccount.php) 2-insert customer id customer id:847 96 | the filed isn't accept data and will return error message | the filed isn't accept data but return wrong error message (Characters are not allowed) | major | medium |  | Sayed | new
22 | when I add valid data for account num to edit account the page crashed | 1-open URL (https://demo.guru99.com/V4/ manager/editAccount.php) 2-insert account num -account num :135751 | the account num page will navigate to open new page to edit account | the page crashed and return error message (This page isn’t workingdemo.guru99.com is currently unable to handle this request. HTTP ERROR 500) | critical | high |  | Mostafa | new
23 | when I delete an account it display confirmation when I click ok page will crash | 1-open URL (https://demo.guru99.com/V4/ manager/deleteAccountInput.php) 2-insert account num -account num:135755 | account num will delete with confirmation message | account num filed display confirmation message but page crashed | critical | high |  | Mostafa | new
24 | when I add deposit with valid data page crashed | 1-open URL (https://demo.guru99.com/V4/ manager/DepositInput.php) 2-insert account num -account num:135755 3-insert amount -amount:100 4-insert description -description:new dpst 5-click submit | deposit will add to account and will return confirmation message | page crashed and return error message (This page isn’t workingdemo.guru99.com is currently unable to handle this request. HTTP ERROR 500) | critical | high |  | Mostafa | new
25 | when I do withdrawal for manager role I found not handle confirmation message for Transaction ID | 1-open URL (https://demo.guru99.com/V4/manager/WithdrawalInput.php) 2-insert account num -account num :135757 3-insert amount -amount:1000 4-insert description Desc: new WD 5-click submit | cash will withdraw and will return confirmation message | the page accept data and do withdrawal successfully but return not handle confirmation message | critical | high |  | Alaa | new
26 | when I add account num to do Balance Enquiry page crashed | 1-open URL (https://demo.guru99.com/V4/ manager/BalEnqInput.php) 2-insert account num -account num:135766 3-click submit | balance will display out | balance isn't display out with crash and return error message (This page isn’t workingdemo.guru99.com is currently unable to handle this request. HTTP ERROR 500) | critical | high |  | Mostafa | new
27 | when I insert data to do mini statement I found white blank page | 1-open URL (https://demo.guru99.com/V4 /manager/MiniStatementInput.php) 2-insert account num -account num :135770 3-click submit | page will show last 5 transactions of an account | the page show as white blank page | critical | high |  | Mostafa | new
28 | when I insert data to do customize statement I found white blank page | 1-open URL (https://demo.guru99.com/V4/manager /CustomisedStatementInput.php) 2-insert accountnum -account num :135770 3-insert from date -from date:1/1/2022 4-insert from date 5-insert to date -to date:1/1/2023 6-insert Minimum Transaction Value -minimum transation:1000 7-insert Number of Transaction -number of transation:3 8-click submit | statement will customized and return confirmation message | statement isn't customized and return white blank page | critical | high |  | Mostafa | new
29 | when I skip Transaction Value in customized statement I found it isn't mandatory | 1-open URL (https://demo.guru99.com/V4 /manager/MiniStatementInput.php) 2-skip Transaction Value 3-click submit | minimum transition is a mandatory filed and will return error message if left blank | filed isn't return error message | major | low |  | Alaa | new
30 | when I skip Transaction Value in customized statement I found it isn't mandatory | 1-open URL (https://demo.guru99.com/V4 /manager/MiniStatementInput.php) 2-skip Number of Transaction 3-click submit | number of transaction is a mandatory filed and will return error message | filed isn't return error message | major | low |  | Alaa | new
31 | when I add from date after to date it accept this wrong date | 1-open URL 2-insert invalid accountnum 3-insert from date -account num :1357705 4-insert from date 5-insert to date -to date:1/1/2024 6-insert Minimum Transaction Value -minimum transation:1000 7-insert Number of Transaction -number of transation:3 8-click submit | filed will return error message | filed isn't return error message and continuous as valid data | critical | medium |  | Sayed | new
32 | when I login with valid data I click back it back to login page | 1-open URL (https://demo.guru99.com/V4/) 2-insert user name -Userid:mngr576619 3-insert password -password:@7mD 4-click Login 5-clcick back | page can't back | page back | major | high |  | Mostafa | new
33 | when I click login without any data page return wrong error message | 1-open URL (https://demo.guru99.com/V4/) 2-skip user name 3-skip password 4-click Login | login page will return error message | login page return wrong error message (User or Password is not valid) | minor | low |  | Mostafa | new
34 | when I logout and click back page will return to home page after logout | 1-open ur (https://demo.guru99.com/V4/ manager/Managerhomepage.php) 2-click logout 3-click back | home page isn't back after logout | home page is back after logout | critical | high |  | Mostafa | new
customer role
35 | when I do Balance enquiry for customer role page crashed | 1-open URL (https://demo.guru99.com/V4/ customer/BalEnqInput.php) 2-select account num 3-Click submit | balance enquiry will display | Balance enquiry page crashed | critical | high |  | Alaa | new
36 | when I do fund transfer it return confirmation message without transfer id | 1-open URL (https://demo.guru99.com/V4/ customer/customerfundinput.php) 2-insert Payers account no -Payers account no:135770 3-insert Payees account no -Payees account no:135771 4-insert amount -Amount:1000 5-isnert Desc -Description: Newt 6-click submit | the fund will transfer and will return confirmation message | fund transferred but return wrong confirmation message | major | low |  | Sayed | new
37 | when I insert old password and try to change password I don't found strong password option | 1-open URL (https://demo.guru99.com/V4/ manager/PasswordInput.php) 2-insert old password -oldpassword:123456 | new password filed have strong password option | new password filed don't have strong password option | minor | low |  | Sayed | new
38 | when I add valid account num for mini statement it return white blank page | 1-open URL (https://demo.guru99.com/V4/ customer/MiniStatementInput.php) 2- insert account num account num :135771 3-click submit | the mini statement for this account will display | the mini statement isn't display and navigate to white blank page | critical | high |  | Mostafa | new
39 | when I insert valid data to customized statement page it return white blank page | 1-open URL (https://demo.guru99.com/V4/customer/CustomisedStatementInput.php) 2-insert account no -account num :135771 3-insert from date -from date:1/1/2022 4-insert to date -to date:1/1/2023 5-insert minimum transaction value -minimum transaction:1000 6-number of transaction -number of transaction:3 7-click submit | this statement will display | customized statement return white blank page | critical | high |  | Alaa | new
40 | when I skip Transaction Value in customized statement I found it isn't mandatory | 1-open URL (https://demo.guru99.com/V4/customer/CustomisedStatementInput.php) 2-insert account no -account num :135771 3-insert from date -from date:1/1/2022 4-insert to date -to date:1/1/2023 5-skip minimum transaction value 6-number of transaction -number of transaction:3 7-click submit | the filed is a mandatory filed and will return error message | the filed isn't mandatory and don't return any error message and continuous as valid data | major | low |  | Alaa | new
41 | when I skip Number of Transaction in customized statement I found it isn't mandatory | 1-open URL (https://demo.guru99.com/V4/customer/CustomisedStatementInput.php) 2-insert account no -account num :135771 3-insert from date -from date:1/1/2022 4-insert to date 5-insert minimum transaction value -minimum transaction:1000 6-skip number of transaction 7-click submit | the filed is mandatory and will return error message | the filed isn't mandatory and don't return any error message and continuous as valid data | major | low |  | Alaa | new
42 | when I add from date greater than to date it accept this wrong logical date | 1-open URL (https://demo.guru99.com/V4/customer/CustomisedStatementInput.php) 2-insert account no -account num :135771 3-insert from date -from date:1/1/2023 4-insert to date -to date:1/1/2022 5-insert minimum transaction value minimum transaction:1000 6-number of transaction -number of transaction:3 7-click submit | the page will return error message | page continuous as valid data and don't return any error message | major | medium |  | Mostafa | new